## 0.Overview
SWP391 — Project AI Usage Report
Subject Code | SWP391
Subject Name | Software Development Project
Class Code | SE20A01
Semester | Summer 2026
Lecturer Name | HanhNT54
Group Code | team_4
Project Title | Beauty Salon Management System (BSMS)
List of Students
No | StudentCode | StudentName | Role In Group | AI Tool Used
1 | DE190464 | KienDG | Leader / Full-stack developer | ChatGPT, GitHub Copilot, Gemini
2 | DE190479 | TungHT | Developer / Tester | ChatGPT, GitHub Copilot
3 | DE190428 | NamDT | Developer | ChatGPT, Copilot
4 | DE190087 | ToanNN | Developer / Documentation | ChatGPT,Gemini
5 | DE190542 | TuyenNHM | QA / Documentation | ChatGPT,Gemini

## Week 1
Week 1 (26/05–01/06)
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1 | Requirement | Actors & use-case brainstorming | ChatGPT | Draft list of actors and ~60 use cases | Kept 5 actors, curated to 66 UCs matching salon scope | Group_W1_UseCases (drive) | 66 UCs finalized | 4 | Some generic UCs not relevant to a salon
2 | Requirement | Business rules drafting | ChatGPT | ~30 candidate business rules | Selected/rewrote to BR-01..BR-99 with real constraints | Group_W1_BR (drive) | 26 BRs kept | 4 | Needed manual alignment with DB constraints
3 | Design | Initial ERD proposal | ChatGPT | Suggested core tables & relationships | Adjusted PK/FK, added 45 real tables & CHECKs | Group_W1_ERD (drive) | 45 tables | 4 | Missed some link tables & status enums

## Week 2
Week 2 (02/06–08/06)
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1 | Design | Layered backend architecture | ChatGPT | Route→Controller→Service module template | Adopted pattern; added mssql pool + transactions | Group_W2_Arch (drive) | 20 modules scaffolded | 5 | Suggested repository layer we chose to skip
2 | Implementation | Auth module (JWT, bcrypt, OTP) | GitHub Copilot | Boilerplate for register/login/verify | Reworked SQL to SQL Server, fixed OTP expiry logic | commit 'Upload Beauty Salon System' | auth.service ~450 LOC | 4 | Generated MySQL-style SQL initially
3 | Implementation | React auth pages | Copilot | Login/Register/Verify components | Wired to axiosClient + Context, added validation | frontend/src/pages/auth | 5 pages | 4 | Styling needed manual overrides

## Week 3
Week 3 (09/06–15/06)
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1 | Implementation | Booking slot algorithm | ChatGPT | Slot-generation from shifts − busy intervals | Implemented calculateSlotsInternal, added 08:00–20:00 rule | availability.service.js | ~470 LOC | 5 | Edge cases around buffer time fixed manually
2 | Implementation | Appointment state machine | ChatGPT | 6-state transition map | Adopted VALID_TRANSITIONS + mapStatus for legacy states | appointment-state.service.js | 6 states, 8 transitions | 5 | Legacy DB statuses had to be mapped

## Week 4
Week 4 (16/06–22/06)
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1 | Implementation | VNPay integration | ChatGPT | HMAC-SHA512 signing + param sorting | Verified vnp_SecureHash, added IPN/return handlers | payments.service.js | createVnpayPaymentUrl + callback | 4 | Signature ordering subtle; verified against docs
2 | Testing | Unit tests for auth.service | Copilot | Jest test skeletons | Expanded to 24 TCs incl. Google login & reset | tests/unit/auth.service.test.js | 24 TCs pass | 5 | Mock setup for mssql pool needed fixing
3 | Testing | Receptionist API integration tests | Copilot | Supertest request templates | Wrote 16 integration TCs | tests/integration/ | 16 TCs pass | 4 | DB state isolation handled manually

## Week 5
Week 5 (23/06–29/06)
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1 | Implementation | Waiting list match & hold | ChatGPT | Queue + hold-expiry approach | Implemented MATCHED + HoldExpiresAt with UTC | waiting-list.service.js | match/hold/expire | 4 | Timezone handling required GETUTCDATE
2 | Implementation | Receptionist dashboard | Copilot | Grid layout + component stubs | Built cockpit: occupancy, dispatcher, timeline, finance | ReceptionistDashboard.jsx | 1 cockpit screen | 4 | Heavy manual CSS/layout tuning

## Week 6
Week 6 (06/07–12/07)
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1 | Implementation | Membership & loyalty engine | ChatGPT | Rank-from-points query | Added VIP auto-expire + no-downgrade rule | membership.service.js | tiers + point history | 4 | Timezone bug on VIPExpiredAt fixed
2 | Implementation | Voucher validation (CRM/FREE) | ChatGPT | Discount calc + code checks | Added owner-bound CRM/FREE, min-order, 1-use limit | vouchers.service.js | validateVoucher | 4 | Personalized-code parsing hardened for security
3 | Implementation | AI Stylist & Hair Try-On | Gemini + Replicate | Prompts + model integration | Enforced face verification, pre-filled booking notes | AiStylistAdvisor.jsx | 2 AI features | 4 | Model version hash & simulation mode needed

## Week 7
Week 7 (13/07–19/07)
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1 | Implementation | Admin dashboard & reports | Copilot | Recharts dashboard scaffolds | Built 5 tabs, 8 stat cards; fixed revenue source | AdminDashboard.jsx | 5 tabs | 4 | Packages revenue fixed to PackagePayments
2 | Implementation | AI CRM retention actions | ChatGPT | Churn-risk action suggestions | Made actions executable + auto voucher/email | AdminAiCrm.jsx | CRM actions | 4 | Removed manual phone-call action
3 | Testing | Admin service unit tests | Copilot | Jest stubs for admin services | Completed unit tests across admin modules | tests/unit/admin*.test.js | multiple admin suites | 4 | Repeated mock boilerplate

## Week 8
Week 8 (20/07– )
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1 | Reporting | SDS / RDS documentation | ChatGPT | Draft sections & tables | Rewrote to match real code & 45-table schema | BSMS_SDS / RDS docs | SDS 35p, RDS complete | 4 | Had to correct AI guesses vs actual code
2 | Reporting | Project tracking & issues report | ChatGPT | Backlog & issue templates | Filled from real commit history & test summary | tracking/issues xlsx | ~50 items, 28 issues | 4 | Verified every entry against git log

## Instruction
Column | Description & How to Fill
No. | Sequential number of the log entry (1, 2, 3…).
SDLC Phase | Which phase this AI usage belongs to (Requirement, Design, Implementation, Testing, Reporting).
Task / Activity | Specific task AI was used for (e.g., User Story Development, ERD Design, Workflow Coding, Test Case Generation).
AI Tool Used | Name of the AI tool (ChatGPT, GitHub Copilot, Gemini, etc.).
AI Output | The actual output AI produced (summary only).
Student’s Validation / Modification | How you validated or modified the AI output.
Evidence / Link | Link to a shared folder with screenshots/videos of the AI session. Naming: GroupX_SessionY_Activity.
Quantitative Measure | Numerical evidence of the contribution (user stories, entities, classes, LOC, test cases).
Value Added (1-5) | Self-assessment of AI usefulness (1 = not useful, 5 = very useful).
Risks / Limitations Observed | Limitations/risks observed when using AI.