## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Implement Authentication (register/verify/login) | Register with email OTP, JWT login, forgot/reset password, change password. | 1 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/1 | Closed | KienDG | 2026-06-08 | 2026-06-14 | iter1 | Task, 3_Done | Authentication
Public browsing (services, packages, technicians, promotions) | Guest pages: home, service list/detail, packages, technicians, promotions, contact. | 2 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/2 | Closed | TungHT | 2026-06-08 | 2026-06-14 | iter1 | Task, 3_Done | Service Browsing
Set up SQL Server schema (45 tables) | Create schema.sql with FK and CHECK constraints; seed data. | 3 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/3 | Closed | KienDG | 2026-06-08 | 2026-06-12 | iter1 | Task, 3_Done | Database
Google OAuth login | Sign in / auto-register with a verified Google ID token. | 4 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/4 | Closed | KienDG | 2026-06-16 | 2026-06-20 | iter2 | Task, 3_Done | Authentication
Book Appointment with slot validation | Validate future time, capability, available slots, opening hours, no double-booking. | 5 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/5 | Closed | NamDT | 2026-06-16 | 2026-06-22 | iter2 | Task, 3_Done | Appointment Management
Customer profile & dashboard | Profile edit, avatar upload, personal dashboard. | 6 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/6 | Closed | ToanNN | 2026-06-16 | 2026-06-22 | iter2 | Task, 3_Done | Account Management
Online payment via VNPay & PayOS | Signed VNPay URL + IPN/return, PayOS webhook; invoice paid only after verify. | 7 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/7 | Closed | KienDG | 2026-06-23 | 2026-07-06 | iter3 | Task, 3_Done | Payment
Receptionist operations & dashboard | Walk-ins, check-in/complete/checkout, invoices, refunds, dispatcher. | 8 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/8 | Closed | NamDT | 2026-06-23 | 2026-07-06 | iter3 | Task, 3_Done | Salon Operations
Waiting list match & hold | Join queue; hold a freed slot (HoldExpiresAt) for the first waiting customer. | 9 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/9 | Closed | TuyenNHM | 2026-06-23 | 2026-07-06 | iter3 | Task, 3_Done | Waiting List
Membership & loyalty engine | Derive rank from points; auto-expire temporary VIP; point history. | 10 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/10 | Closed | TungHT | 2026-07-06 | 2026-07-10 | iter4 | Task, 3_Done | Loyalty
Voucher system (save/apply, CRM/FREE) | Validate status/date/min-order; personalized CRM & FREE codes bound to owner. | 11 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/11 | Closed | TungHT | 2026-07-06 | 2026-07-10 | iter4 | Task, 3_Done | Promotion
Treatment Notes V2 + technician attendance | Notes with attachments; attendance and earnings/payout. | 12 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/12 | Closed | ToanNN | 2026-07-06 | 2026-07-08 | iter4 | Task, 3_Done | Treatment Note
AI Stylist Advisor & Virtual Hair Try-On | Gemini morphology analysis and virtual hair try-on with pre-filled booking. | 13 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/13 | Closed | KienDG | 2026-07-08 | 2026-07-09 | iter4 | Feature, 3_Done | AI Support
Admin dashboard overhaul (5 tabs, Recharts) | Stats, monthly revenue, packages, refunds, payouts, attendance. | 14 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/14 | Closed | KienDG | 2026-07-09 | 2026-07-10 | iter4 | Feature, 3_Done | Reporting
Unit & integration tests (Jest) | 54 test cases across auth.service, membershipDiscount and receptionist API. | 15 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/15 | Closed | TuyenNHM | 2026-06-20 | 2026-06-23 | iter2 | Task, 3_Done | Testing
Defect: voucher & reward point double-discount display | Discount shown twice on mount and details views; corrected calculation. | 16 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/16 | Closed | TungHT | 2026-07-10 | 2026-07-10 | iter4 | Defect, 3_Done | Payment
Defect: VIPExpiredAt timezone offset | VIP expiry computed with local time; switched to GETUTCDATE and native JS Date. | 17 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/17 | Closed | TungHT | 2026-07-10 | 2026-07-10 | iter4 | Defect, 3_Done | Loyalty
Defect: infinite page reload loop on membership | Reload loop from updating VIPExpiredAt in membership/customer services. | 18 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/18 | Closed | TungHT | 2026-07-10 | 2026-07-10 | iter4 | Defect, 3_Done | Loyalty
Defect: FullName read from wrong table | Full name pulled from Customers instead of Users table. | 19 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/19 | Closed | ToanNN | 2026-07-10 | 2026-07-10 | iter4 | Defect, 3_Done | Account Management
Defect: unusable vouchers shown in booking/payment | Only usable vouchers should appear; filtered lists in Booking/Payment pages. | 20 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/20 | Closed | TungHT | 2026-07-10 | 2026-07-10 | iter4 | Defect, 3_Done | Promotion
Security: unauthorized use of CRM/free vouchers | Prevent non-owner customers from saving/applying CRM and free-service vouchers. | 21 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/21 | Closed | TungHT | 2026-07-10 | 2026-07-10 | iter4 | Defect, 3_Done | Promotion
Defect: admin dashboard routes point to /receptionist/* | Navigation links corrected to /admin/*. | 22 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/22 | Closed | KienDG | 2026-07-09 | 2026-07-09 | iter4 | Defect, 3_Done | Reporting
Defect: packages revenue miscomputed | Revenue used wrong source; fixed to use PackagePayments. | 23 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/23 | Closed | KienDG | 2026-07-09 | 2026-07-09 | iter4 | Defect, 3_Done | Reporting
Defect: Vietnamese diacritics broken on admin | Restored NVARCHAR/diacritics rendering on admin pages. | 24 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/24 | Closed | ToanNN | 2026-07-09 | 2026-07-09 | iter4 | Defect, 3_Done | Admin
Defect: reward points not deducted on payment confirm | Receptionist payment confirmation now deducts used reward points. | 25 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/25 | Closed | NamDT | 2026-07-10 | 2026-07-10 | iter4 | Defect, 3_Done | Payment
Enhancement: limit voucher usage to 1 per voucher | Enforce maximum voucher usage limit of one time. | 26 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/26 | Closed | TungHT | 2026-07-10 | 2026-07-10 | iter4 | Enhancement, 3_Done | Promotion
Open: consolidate duplicate WaitingList definitions | schema has repeated CREATE TABLE for WaitingList/favorites; needs cleanup. | 27 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/27 | Open | TuyenNHM | 2026-07-18 | 2026-07-25 | iter4 | Task, 2_Doing | Database
Open: replace test VIP 1-minute duration with real policy | Temporary 1-minute VIP used for testing must be set to the production window. | 28 | https://github.com/gnutho1401/Demo-Salon-Spa/-/issues/28 | Open | TungHT | 2026-07-18 | 2026-07-25 | iter4 | Task, 1_To Do | Loyalty

## Summary
BSMS — Issues Report Summary
Metric | Value
Total issues | 28
Closed | 26
Open | 2
Defects | 10
Features/Tasks/Enhancements | 18
Iterations | iter1 – iter4
Repository | https://github.com/gnutho1401/Demo-Salon-Spa