## Product
BSMS — Total Project Tracking (Product Backlog)
Columns A–E filled at project initiation; columns F–J updated at the end of each development iteration.
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Planned | Actual | Update Details
1 | Register / Verify Email | Authentication | Guest | Create an account and confirm it via a 6-digit email OTP (10-minute expiry). | KienDG | Done | iter1 | iter1
2 | Login | Authentication | All users | Email/password login issuing a 1-day JWT; blocks locked/unverified accounts. | KienDG | Done | iter1 | iter1
3 | Google Login | Authentication | Guest, Customer | Sign in / auto-register with a verified Google ID token. | KienDG | Done | iter1 | iter2 | Added in iter2
4 | Forgot / Reset Password | Authentication | All users | Email a reset link (SHA-256 token, 1-hour expiry) and set a new password. | KienDG | Done | iter1 | iter1
5 | Change Password | Account Management | Customer, Staff | Change password after verifying the current one. | ToanNN | Done | iter1 | iter2
6 | Home / Service List / Service Detail | Service Browsing | Guest | Browse services by category and view service details. | TungHT | Done | iter1 | iter1
7 | Package List / Package Detail | Package Browsing | Guest, Customer | Browse combos/treatments and their details. | TungHT | Done | iter1 | iter2
8 | Technicians / Technician Detail | Technician Browsing | Guest | View technicians and their profiles. | TungHT | Done | iter1 | iter1
9 | Promotions | Promotion | Guest | View current promotions and discounts. | TungHT | Done | iter1 | iter2
10 | Contact Support | Support | Guest | Send a contact / support request. | TungHT | Done | iter1 | iter1
11 | Customer Profile / Edit / Avatar | Account Management | Customer | View and update personal info and avatar. | ToanNN | Done | iter1 | iter2
12 | Customer Dashboard | Account Management | Customer | Personal dashboard: upcoming appointments, points, recommendations. | ToanNN | Done | iter2 | iter2
13 | Book Appointment | Appointment Management | Customer | Book by service, technician, date/time with slot & opening-hour validation. | NamDT | Done | iter2 | iter2
14 | My Appointments / Detail | Appointment Management | Customer | List and view details/history of appointments. | NamDT | Done | iter2 | iter2
15 | Reschedule Appointment | Appointment Management | Customer | Request a new slot for an existing appointment. | NamDT | Done | iter2 | iter2
16 | Payment (VNPay/PayOS) | Payment | Customer | Pay for an appointment online via VNPay/PayOS with callback verification. | KienDG | Done | iter2 | iter2
17 | Payment History / Result | Payment | Customer | View payment history and the gateway result page. | KienDG | Done | iter2 | iter2
18 | Membership & Loyalty | Loyalty | Customer | View rank, points, discount and progress to the next level. | TungHT | Done | iter2 | iter2
19 | Vouchers | Promotion | Customer | Browse, save and apply vouchers (incl. personalized CRM/FREE codes). | TungHT | Done | iter3 | iter3
20 | Customer Packages / Usage | Package | Customer | Buy combos and track remaining sessions/usage. | TungHT | Done | iter2 | iter2
21 | Feedback | Feedback | Customer | Send feedback / complaints about services. | TuyenNHM | Done | iter2 | iter2
22 | Review | Feedback | Customer | Rate a completed appointment (service + technician) with images. | TuyenNHM | Done | iter3 | iter3
23 | Favorites | Account Management | Customer | Favorite services and technicians. | TuyenNHM | Done | iter3 | iter3
24 | Notifications | Notification | All users | Inbox of system notifications and appointment reminders. | ToanNN | Done | iter3 | iter3
25 | Waiting List | Queue Management | Customer | Join a waiting list and get a freed slot held for booking. | TuyenNHM | Done | iter3 | iter3
26 | AI Assistant (Chat) | AI Support | Customer | Chat assistant (Gemini) for consultation and booking help. | KienDG | Done | iter3 | iter3
27 | AI Stylist Advisor / Hair Try-On | AI Support | Customer | AI morphology analysis and virtual hair try-on. | KienDG | Done | iter3 | iter3
28 | AI Skin Analyzer | AI Support | Customer | AI skin analysis with service suggestions. | KienDG | Done | iter3 | iter3
29 | Receptionist Dashboard | Salon Operations | Receptionist | Single-screen cockpit: room occupancy, KTV dispatch, timeline, finance. | NamDT | Done | iter3 | iter3
30 | Create Appointment / Walk-in | Appointment Management | Receptionist | Create bookings and walk-ins for customers. | NamDT | Done | iter2 | iter2
31 | Check-in / Start / Complete / Checkout | Appointment Operation | Receptionist | Drive appointments through their operational states. | NamDT | Done | iter3 | iter3
32 | Invoices / Mark-Paid / Refund | Invoice | Receptionist | Create invoices, mark paid at counter and process refunds. | NamDT | Done | iter3 | iter3
33 | Manage Customers | Customer Profile | Receptionist | Create, search and update customer profiles. | NamDT | Done | iter2 | iter2
34 | Technician Dispatcher | Staff Coordination | Receptionist | Assign/redispatch technicians for appointments. | NamDT | Done | iter3 | iter3
35 | Reschedule Requests | Support Request | Receptionist | Handle technician/customer reschedule requests. | NamDT | Done | iter3 | iter3
36 | Technician Dashboard / Schedule | Schedule | Technician | View assigned schedule and appointments. | NamDT | Done | iter2 | iter2
37 | Technician Appointments / Detail | Appointment Status | Technician | View and update the status of assigned appointments. | NamDT | Done | iter3 | iter3
38 | Treatment Notes V2 | Treatment Note | Technician | Record treatment notes and attachments per appointment. | ToanNN | Done | iter3 | iter3
39 | Technician Attendance | Employee Management | Technician | Attendance check-in/out and timesheet. | TuyenNHM | Done | iter3 | iter3
40 | Technician Earnings | Reporting | Technician | View commission/tip earnings and payout requests. | ToanNN | Done | iter3 | iter3
41 | Admin Dashboard | Reporting | Manager/Admin | 5-tab dashboard: stats, monthly revenue, packages, refunds, payouts. | KienDG | Done | iter3 | iter3
42 | Admin Employees / Work Shifts | Employee Management | Manager/Admin | CRUD employees, assign services and work shifts. | ToanNN | Done | iter3 | iter3
43 | Admin Services / Categories | Service Management | Manager/Admin | CRUD services and service categories. | ToanNN | Done | iter2 | iter2
44 | Admin Packages | Package Management | Manager/Admin | CRUD service packages/combos. | ToanNN | Done | iter2 | iter2
45 | Admin Promotions / Vouchers | Promotion Management | Manager/Admin | CRUD promotions and vouchers. | ToanNN | Done | iter3 | iter3
46 | Admin Memberships | Membership Management | Manager/Admin | CRUD membership levels. | ToanNN | Done | iter2 | iter2
47 | Admin Users | System Management | Manager/Admin | Create accounts and manage user permissions. | ToanNN | Done | iter3 | iter3
48 | Admin System Logs | System Management | Manager/Admin | View user actions and system activity history. | TuyenNHM | Done | iter3 | iter3
49 | Admin Reports | Reporting | Manager/Admin | Business reports: revenue, appointments, services, employees. | KienDG | Done | iter3 | iter3
50 | Admin Reviews / Feedbacks | Feedback | Manager/Admin | Moderate reviews and handle feedback. | TuyenNHM | Done | iter3 | iter3
51 | Admin Refunds | Payment | Manager/Admin | Review and process refund requests. | TuyenNHM | Done | iter3 | iter3
52 | Admin AI CRM / Monitoring | AI System | Manager/Admin | AI churn/retention actions and AI usage monitoring. | KienDG | Done | iter3 | iter3
no | Full name | Student ID | Effort (%)
1 | Duong Gia Kien (KienDG) | DE190464 | 22%
2 | Nguyen Nhat Toan (ToanNN) | DE190087 | 20%
3 | Ho Thang Tung (TungHT) | DE190479 | 19%
4 | Do Tien Nam (NamDT) | DE190428 | 20%
5 | Nguyen Hoang Minh Tuyen (TuyenNHM) | DE190542 | 19%

## Iter1
Iteration Tracking — Iteration 1
Columns A–D copied from Product; columns E–I updated/filled by the end of the iteration.
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Register / Verify Email | Authentication | Account creation with email OTP verification. | KienDG | Done | II.1 | II.1.1
2 | Login | Authentication | JWT login with role & membership. | KienDG | Done | II.1 | II.1.2
3 | Forgot / Reset Password | Authentication | Reset link with hashed token. | KienDG | Done | II.1 | II.1.5
4 | Home / Service List / Detail | Service Browsing | Public service catalog and details. | TungHT | Done | II.2 | II.4.1
5 | Technicians / Detail | Technician Browsing | Public technician list & profiles. | TungHT | Done | II.4 | II.6.1
6 | Contact Support | Support | Guest contact/support form. | TungHT | Done | II.5 | II.5.4

## Iter2
Iteration Tracking — Iteration 2
Columns A–D copied from Product; columns E–I updated/filled by the end of the iteration.
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Google Login | Authentication | Google OAuth sign-in / auto-register. | KienDG | Done | II.1 | II.1.2
2 | Change Password | Account Management | Change password after verifying current. | ToanNN | Done | II.1 | II.1.4
3 | Customer Profile / Edit / Avatar | Account Management | Profile & avatar management. | ToanNN | Done | II.6 | II.5.1
4 | Customer Dashboard | Account Management | Personal dashboard: upcoming appts, points. | ToanNN | Done | II.6 | II.5.2
5 | Package List / Detail | Package Browsing | Combo catalog and details. | TungHT | Done | II.10 | II.8.3
6 | Promotions | Promotion | Public promotions listing. | TungHT | Done | II.3 | II.8.1
7 | Book Appointment | Appointment Management | Slot & opening-hour validated booking. | NamDT | Done | II.7 | II.2.2
8 | My Appointments / Detail | Appointment Management | Appointment list, detail & history. | NamDT | Done | II.7 | II.2.3
9 | Reschedule Appointment | Appointment Management | Request new slot for existing appointment. | NamDT | Done | II.7 | II.2.3
10 | Payment (VNPay/PayOS) | Payment | Online payment with callback verification. | KienDG | Done | II.8 | II.3.1
11 | Payment History / Result | Payment | Payment history & gateway result. | KienDG | Done | II.8 | II.3.5
12 | Membership & Loyalty | Loyalty | Rank, points and next-level progress. | TungHT | Done | II.9 | II.7.1
13 | Customer Packages / Usage | Package | Buy combos and track sessions. | TungHT | Done | II.10 | II.8.4
14 | Feedback | Feedback | Send feedback / complaints. | TuyenNHM | Done | II.11 | II.5.4
15 | Receptionist: Create Appt / Manage Customers | Salon Operations | Front-desk booking and customer management. | NamDT | Done | II.14 | II.5.6
16 | Technician Dashboard / Schedule | Schedule | Assigned schedule & appointments. | NamDT | Done | II.22 | II.6.3
17 | Admin Services / Categories | Service Management | Master-data CRUD for services. | ToanNN | Done | II.27 | II.4.2
18 | Admin Packages | Package Management | Master-data CRUD for service packages. | ToanNN | Done | II.28 | II.8.3
19 | Admin Memberships | Membership Management | Master-data CRUD for membership levels. | ToanNN | Done | II.30 | II.7.2

## Iter3
Iteration Tracking — Iteration 3
Columns A–D copied from Product; columns E–I updated/filled by the end of the iteration.
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Vouchers (save/apply, CRM/FREE) | Promotion | Voucher validation incl. personalized codes. | TungHT | Done | II.29 | II.8.2
2 | Review (service + technician + images) | Feedback | Post-appointment review with images. | TuyenNHM | Done | II.11 | II.5.3
3 | Favorites | Account Management | Favorite services and technicians. | TuyenNHM | Done | II.6 | II.5.5
4 | Notifications & Reminders | Notification | Inbox + scheduled appointment reminders. | ToanNN | Done | II.12 | II.10.2
5 | Waiting List (match & hold) | Queue Management | Join queue and hold a freed slot. | TuyenNHM | Done | II.18 | II.9.4
6 | AI Assistant / Stylist / Skin | AI Support | Gemini chat, hair try-on, skin analysis. | KienDG | Done | II.13 | II.10.4
7 | Receptionist Dashboard (cockpit) | Salon Operations | Unified single-screen operations cockpit. | NamDT | Done | II.15 | II.9.1
8 | Check-in/Start/Complete/Checkout | Appointment Operation | Full operational state machine execution. | NamDT | Done | II.15 | II.9.2
9 | Invoices / Mark-Paid / Refund | Invoice | Invoicing, counter payment & refunds. | NamDT | Done | II.21 | II.9.3
10 | Technician Dispatcher | Staff Coordination | Assign and redispatch technicians. | NamDT | Done | II.16 | II.9.1
11 | Reschedule Requests | Support Request | Handle reschedule and support requests. | NamDT | Done | II.25 | II.2.3
12 | Technician Appointments / Detail | Appointment Status | View/update assigned appointment status. | NamDT | Done | II.24 | II.2.5
13 | Treatment Notes V2 | Treatment Note | Notes & attachments per treatment. | ToanNN | Done | II.20 | II.9.2
14 | Technician Attendance | Employee Management | Attendance check-in/out and timesheet. | TuyenNHM | Done | II.26 | II.6.3
15 | Technician Earnings | Reporting | Commission/tip earnings & payouts. | ToanNN | Done | II.32 | II.10.1
16 | Admin Dashboard | Reporting | 5-tab dashboard: stats, revenue, payouts. | KienDG | Done | II.32 | II.10.1
17 | Admin Employees / Work Shifts | Employee Management | CRUD employees & assign work shifts. | ToanNN | Done | II.26 | II.6.2
18 | Admin Promotions / Vouchers | Promotion Management | CRUD promotions and vouchers. | ToanNN | Done | II.29 | II.8.1
19 | Admin Users | System Management | Create accounts and manage permissions. | ToanNN | Done | II.31 | II.1.1
20 | Admin System Logs | System Management | View user actions and activity logs. | TuyenNHM | Done | II.31 | II.1.3
21 | Admin Reports | Reporting | Business reports: revenue, appts, KTV. | KienDG | Done | II.32 | II.10.1
22 | Admin Reviews / Feedbacks | Feedback | Moderate reviews and handle feedback. | TuyenNHM | Done | II.11 | II.5.4
23 | Admin Refunds | Payment | Review and process refund requests. | TuyenNHM | Done | II.8 | II.3.4
24 | Admin AI CRM / Monitoring | AI System | AI retention actions & monitoring. | KienDG | Done | II.32 | II.10.4